## 1. Summary
Overall for all topics(Including E-Application, OSS, JS Component)
Table A - Summary of Price Calculation Matrix
Category | 2019 |  | 2020 |  | 2021
| PD | Cost | PD | Cost | PD | Cost
1. System Build Cost(One time) | 467 | 0 |  | 0 |  | 0
2. Additional Cost...(One time) |  | 0 |  | 0 |  | 0
3. Operation Cost | 0 | 0 | 0 | 0 | 0 | 0
4. System Maintenance | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 467 | 0 | 0 | 0 | 0 | 0
Table C - Story Price Calculation Matrix
Category | 2018 |  |  |  |  | 2019 |  |  |  |  | 2020 |  |  |  | 2021
| S | M | L | XL | XXL | S | M | L | XL | XXL | S | L | XL | XXL | S | M | L | XL | XXL
Story Sizing | 0 | 0 | 0 | 0 | 0 | 16 | 22 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PD | 0 | 0 | 0 | 0 | 0 | 96 | 176 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Table B - PD of System Build Matrix | bar: 2018 S to 2018 M
Skill Level | 2018 S: PD; 2018 M: PD/Build PD
D1 | 2018 S: 83; 2018 M: 17.77%
D2 | 2018 S: 34; 2018 M: 7.281%
D3 | 2018 S: 26; 2018 M: 5.567%
B1 | 2018 S: 203; 2018 M: 43.47%
B2 | 2018 S: 121; 2018 M: 25.91%
Table C - Story Complexity to Price Calculation Matrix | bar: 2018 S to 2020 S
Story Complexity | 2018 S: Days D1; 2018 L: PD D2; 2018 XXL: PD D3; 2019 M: PD B1; 2019 XL: PD B2; 2020 S: Total PDs
S | 2018 S: 1; 2018 M: 16.67%; 2018 L: 0.5; 2018 XL: 8.333%; 2018 XXL: 0; 2019 S: 0%; 2019 M: 2.5; 2019 L: 41.67%; 2019 XL: 2; 2019 XXL: 33.33%; 2020 S: 6
M | 2018 S: 1; 2018 M: 12.5%; 2018 L: 0.5; 2018 XL: 6.25%; 2018 XXL: 0.5; 2019 S: 6.25%; 2019 M: 4; 2019 L: 50%; 2019 XL: 2; 2019 XXL: 25%; 2020 S: 8
L | 2018 S: 3; 2018 M: 23.08%; 2018 L: 1; 2018 XL: 7.692%; 2018 XXL: 1; 2019 S: 7.692%; 2019 M: 5; 2019 L: 38.46%; 2019 XL: 3; 2019 XXL: 23.08%; 2020 S: 13
XL | 2018 S: 3; 2018 M: 18.75%; 2018 L: 2; 2018 XL: 12.5%; 2018 XXL: 1; 2019 S: 6.25%; 2019 M: 5; 2019 L: 31.25%; 2019 XL: 5; 2019 XXL: 31.25%; 2020 S: 16
XXL | 2018 S: 6; 2018 M: 21.43%; 2018 L: 4; 2018 XL: 14.29%; 2018 XXL: 2; 2019 S: 7.143%; 2019 M: 8; 2019 L: 28.57%; 2019 XL: 8; 2019 XXL: 28.57%; 2020 S: 28

## 2. Quotation
Quotation for E-Application One time setup & Maintance &Application
1. System Build
Offering Party
Company | Vendor Name
Project | eApplication
Date & Revision
Table A - Skill Level Rate |  |  |  | Table B - Story Complexity to Price Calculation Matrix
| Skill | Rate / Day |  | Story Complexity | Days D1 | Days D2 | Days D3 | Days B1 | Days B2 | Total PDs | Total Story Price
Skill/Location 1 | D1 | 0 |  | S | 1 | 0.5 | 0 | 2.5 | 2 | 6 | 0
Skill/Location 2 | D2 | 0 |  | M | 1 | 0.5 | 0.5 | 4 | 2 | 8 | 0
Skill/Location 3 | D3 | 0 |  | L | 3 | 1 | 1 | 5 | 3 | 13 | 0
Skill/Location 4 | B1 | 0 |  | XL | 3 | 2 | 1 | 5 | 5 | 16 | 0
Skill/Location 5 | B2 | 0 |  | XXL | 6 | 4 | 2 | 8 | 8 | 28 | 0
Table C - Supplier Story Volumes per Time Frame [Informative] | [8 empty] | Role | PDs
Sr# | Sprint | S | M | L | XL | XXL | Block Price |  | D1 | 83
1 | S1 | 3 | 1 | 2 | 0 | 0 | 0 |  | D2 | 34
2 | S2 | 0 | 3 | 0 | 0 | 0 | 0 |  | D3 | 26
3 | S3 | 1 | 1 | 1 | 0 | 0 | 0 |  | B1 | 203
4 | S4 | 0 | 2 | 3 | 0 | 0 | 0 |  | B2 | 121
5 | S5 | 0 | 3 | 0 | 0 | 0 | 0
6 | S6 | 0 | 1 | 1 | 0 | 0 | 0
7 | S7 | 0 | 1 | 1 | 0 | 0 | 0
8 | S8 | 0 | 1 | 1 | 0 | 0 | 0
9 | S9 | 1 | 2 | 0 | 0 | 0 | 0
10 | S10 | 0 | 2 | 2 | 0 | 0 | 0
11 | S11 | 1 | 0 | 2 | 0 | 0 | 0
12 | S12 | 4 | 1 | 0 | 0 | 0 | 0
13 | S13 | 2 | 1 | 1 | 0 | 0 | 0
14 | S14 | 2 | 1 | 1 | 0 | 0 | 0
15 | S15 | 2 | 2 | 0 | 0 | 0 | 0
TOTAL |  | 16 | 22 | 15 | 0 | 0 | 0
Total PD |  | 96 | 176 | 195 | 0 | 0 | 467
Avg. Dayrate |  | 0 | 0 | 0 | 0 | 0 | 0
Table D - Project Total Prices
Backlog | 0
License Fee | 0
Knowledge Transfer | 0
0 | 0
0 | 0
Final Price | 0
2. Application Maintenance
Table E - Maintenance
Year | PD(Month *PD) | Skill Level | Daily Rate | Subtotal (incl. VAT)
2019 | 0 | B2 | 0 | 0
2020 | 0 | B2 | 0 | 0
2021 | 0 | B2 | 0 | 0
Final Price |  |  |  | 0
3. Application Operation
Table F - Operation
Year | PD(Month *PD) | Skill Level | Daily Rate | Subtotal (incl. VAT)
2019 | 0 | B2 | 0 | 0
2020 | 0 | B2 | 0 | 0
2021 | 0 | B2 | 0 | 0
Final Price |  |  |  | 0
Table G - Operation License Fee |  |  |  |  | Table H -Total Operation Fee
Year | Scope | Price | Subtotal (incl. VAT) |  | Year | Subtotal (incl. VAT)
2019 |  | 0 | 0 |  | 2019 | 0
2020 |  | 0 | 0 |  | 2020 | 0
2021 |  | 0 | 0 |  | 2021 | 0
Final Price |  |  | 0 |  | Final Price | 0
Usage Notes
Supplier | Supplier Input fields are highlighted with a green background
1 | Specifiy daily rates used (e. g. B3 Nearshore) for the proposal and fill out daily rates in Table A
2 | Specify total days required by each skill to complete one user story in Table B
3 | Fill out "complexity" in sheet "Work Breakdown" for each User Story
4 | Optional: Add fix price packages in sheet "4 Workpackages"
BMW Project Team | Fields with yellow background have to be filled out by BMW project team
1 | In Table Center the total amounT of stories expected for Releases 2 -N. This does not include stories included to Release 1
2 | Enter user stories for release 1 in sheet "3. Backlog"
3 | Enter all EPICs in sheet "3. Backlog"

## A1. OSS Quotation
Quotation for OSS Maintance and Application Operation
Offering Party
Company | Vendor Name
Project | eApplication
Date & Revision | 09.13.2018
1. Application Maintenance
Table A - Maintenance
Year | PD | Skill Level | Daily Rate | Subtotal (incl. VAT)
2019 | 0 | B2 | 0 | 0
2020 | 0 | B2 | 0 | 0
2021 | 0 | B2 | 0 | 0
Final Price |  |  |  | 0
2. Application Operation
Table F - Operation
Year | PD | Skill Level | Daily Rate | Subtotal (incl. VAT)
2019 | 0 | B2 | 0 | 0
2020 | 0 | B2 | 0 | 0
2021 | 0 | B2 | 0 | 0
Final Price |  |  |  | 0

## A2. JS Component Quotation
Quotation for JS Component(Front end of SF web calculator) Maintance and Application Operation
Offering Party
Company | Vendor Name
Project | eApplication
Date & Revision | 09.13.2018
1. Application Maintenance
Table A - Maintenance
Year | PD | Skill Level | Daily Rate | Subtotal (incl. VAT)
2019 | 0 | B2 | 0 | 0
2020 | 0 | B2 | 0 | 0
2021 | 0 | B2 | 0 | 0
Final Price |  |  |  | 0
2. Application Operation
Table F - Operation
Year | PD | Skill Level | Daily Rate | Subtotal (incl. VAT)
2019 | 0 | B2 | 0 | 0
2020 | 0 | B2 | 0 | 0
2021 | 0 | B2 | 0 | 0
Final Price |  |  |  | 0

## 3. Backlog
Epic | User Story | Title | Epic / Story Description | Impl | Year | Sprint | Story Definition Mode | Release / Stage | Complexity | Required Epics | Examples and Specs Subfolder | Price
EPIC 1 |  | Entry Point: Stand alone |  | SUP |  |  | EPIC |  |  |  |  | 0
| 1-1 | App development | As a user of eAPP, I want to deploy a standalone entry point for eAPP so that eAPP user can select vehicle and SF product directly from eAPP.. | SUP | 2019 | S1 | Story |  | S |  |  | 0
EPIC 2 |  | App download |  | SUP |  |  | EPIC |  |  |  |  | 13
| 2-1 | QR code to download | As a user of eAPP, I want to scan a QR code so that I can download and open the APP to start the application. | SUP | 2019 | S1 | Story |  | L |  |  | 13
| 2-2 | QR code scan | As a user of eAPP, I want to scan a QR code in eApp so that I can prefill information in eApp |  | 2019 | S1 | Story |  | L
| 2-3 | QR generate | As BMW eapp owner, I want to generate the QR code with predefined information. So that user can scan it then download the app or load the page with predefined information. | SUP | 2019 | S2 | Story |  | M |  |  | 0
EPIC 3 |  | Registration & Login |  | SUP |  |  | EPIC |  |  |  |  | 6
| 3-1 | Register | As a New user to BMW Easy Finance APP I should be able to Register with temp. pwd.So that I can create a new Account for Easy Finance APP. | SUP | 2019 | S1 | Story |  | S |  |  | 0
| 3-2 | Login | As a Existing User of Easy Finance APP When I trying to Register with Easy Application FinanceI should be prompted to login.So that I can login using my existing Account and access Easy Finance App successfully. | SUP | 2019 | S1 | Story |  | M |  |  | 0
| 3-3 | Login | As a user using Esay finance APP keep login status after I have login with other BMW systems I can access Esay Finance APP very fast without addtional login | SUP | 2019 | S1 | Story |  | S |  |  | 6
EPIC 4 |  | Products Selection (Dealer & Vehicle) |  | SUP |  |  | EPIC |  |  |  |  | 22
| 4-1 | Select vehicle | As a user, I want to select the vehicle So that I can start the finance application process | SUP | 2019 | S2 | Story |  | M |  |  | 8
| 4-2 | Select dealer | As a user, I want to chose the dealership of the car I would like to purchase / finance. So that I can continue the process later on in my next visit. So that I can get the dealer specific vehicle / finance product | SUP | 2019 | S2 | Story |  | M |  |  | 8
| 4-3 | Get quotation price | As a user, I want to adjust the MSRP to the agreed quotation price. So that I can finance the quotation price So that I can get a binding offer from the dealer | SUP | 2019 | S3 | Story |  | L |  |  | 0
| 4-4 | Select ASP | As a user I want to add associated products to the finance offer so that I can add vehicle accessories and etc. to the to be financed amount | SUP | 2019 | S3 | Story |  | M |  |  | 8
| 4-5 | Select HIL product | As a user I want to select Herald Leasing products so that i can chose leasing products | SUP | 2019 | S3 | Story |  | S |  |  | 6
| 4-6 | Loyalty offer | As a existing customer and eApp user I want to be able to select the loyalty SF offer so that i can enjoy the loyalty program interest rate subsidy. | SUP | 2019 | S4 | Story |  | M |  |  | 8
EPIC 5 |  | Selected Financial Product |  | SUP |  |  | EPIC |  |  |  |  | 13
| 5-1 | Select SF product | As a user, I want to select the SF Product and adjust the parameter to my needs. So that I can get the SF Product that fits my personal needs | SUP | 2019 | S4 | Story |  | L |  |  | 13
EPIC 6 |  | Binding Offer Management (DFE Review and Audit) |  | SUP |  |  | EPIC |  |  |  |  | 21
| 6-1 | F&I Interaction | As an F&I, I want to review an offer. So that the Application is valid and proceed. | SUP | 2019 | S4 | Story |  | L |  |  | 13
| 6-2 | Customer Interaction | As a user, I want to keep updated in the offer. So that I can go on with the process |  | 2019 | S5 | Story |  | M |  |  | 8
EPIC 7 |  | E-Authetication (PBOC Authorization/NCIIC/Bank Card/Face Recognition/OTP) |  | SUP |  |  | EPIC |  |  |  |  | 13
| 7-1 | Status tracking | a) As a user of eAPP, I want to see the overall E-Application including E-authentication process and required materials, so that I can know the process and prepare materials in advance. | SUP | 2019 | S4 | Story |  | L |  |  | 0
| 7-2 | OCR Scan | b) As BMW SF eAPP Owner, I want the eAPP user to upload PRC ID information for both sides, so that BMW SF can perform NCIIC online identity authentication to the applicant. | SUP | 2019 | S5 | Story |  | M |  |  | 0
| 7-3 | Bank card check | c) As BMW SF eAPP Owner, I want the eAPP user to upload Bank Card information, so that BMW SF can perform China Union Pay online identity authentication to the applicant. | SUP | 2019 | S4 | Story |  | M |  |  | 0
| 7-4 | face recognition | d) As BMW SF eAPP Owner, I want the eAPP user to perform Face Recognition, so that BMW SF can continue to acquire PBOC authorization from the applicant if he/she passed Face Recognition and Vivo Detection. | SUP | 2019 | S5 | Story |  | M |  |  | 0
| 7-5 | Status tracking | e) As BMW SF eAPP Owner, I want to show the E-Authentication Result to the user, so that the user can continue or stop the journey. | SUP | 2019 | S6 | Story |  | M |  |  | 0
| 7-6 | CA authentiation | f) As BMW SF eAPP Owner, I want to generate CA for E-Athentication, so that all the customer actions, including authentication and authorization, can be saved as digital evidence | SUP | 2019 | S6 | Story |  | L |  |  | 13
EPIC 8 |  | Pre Check Management |  | SUP |  |  | EPIC |  |  |  |  | 8
| 8-1 | BMW precheck | a) As an applicant of eAPP, I want to triger pre-check application on the platform after I passed all steps in E-authentication and fulfill the application form, so that I can continue the application process by myself. | SUP | 2019 | S7 | Story |  | M |  |  | 8
| 8-2 | CBO/GU precheck | b) As a co-borrower or guarantor I want to triger pre-check application on the platform using applicant’s account after I passed all steps in E-authentication and fulfill the application form of co-borrower/guarantor part, so that I can continue the application process. As a co-borrower or guarantor I want to triger pre-check application on the platform using applicant’s account after I passed all steps in E-authentication and fulfill the application form of co-borrower/guarantor part, so that I can continue the application process. | SUP | 2019 | S8 | Story |  | L |  |  | 83
| 8-3 | precheck tracking | c) As a dealer FC , I want to see the pre-check application information in DFE once applicant already triger pre-check application, so that I can track all pre-check application status for my customers. | SUP | 2019 | S7 | Story |  | L |  |  | 83
| 8-4 | guideline | d) As an applicant, I want to get the pre-check results (overall result) correctly of myself, co-borrower and guarantor, and also for each status, I can get a clear description on each status and a guideline on next action, so that I can know the meaning of each status and know whether I can continue my application, and what is the next step. | SUP | 2019 | S8 | Story |  | M |  |  | 0
| 8-5 | CBO/GU precheck tracking | e) As an applicant, I want to view the pre-check status of Co-borrower and guarantor, so that I can know more accurate application status. | SUP | 2019 | S9 | Story |  | M |  |  | 0
| 8-6 | redo precheck | f) As an applicant, I want to re-triger the pre-check application on the platform so that if I need to go back to modify some personal information which may have impact on my pre-check result, this platform can support me to re-triger the pre-check application. | SUP | 2019 | S9 | Story |  | S |  |  | 0
| 8-7 | precheck tracking | g) As a dealer FC , I want to see the detail and overall pre-check application result of applicant co-borrower and guarantor in DFE, so that I can track my customer’s application status. | SUP | 2019 | S9 | Story |  | M |  |  | 0
EPIC 9 |  | Application handling (Application Form / co-borrower etc.) |  | SUP |  |  | EPIC
| 9-1 | Complete personal information | a) As a user of eAPP (applicants) I want to fill the personal information as guide step by step, after passed PBOC check so that fill the application form online. | SUP | 2019 | S10 | Story |  | L |  |  | 13
| 9-2 | CBO/GU information | b) As a user of eAPP (applicants)I want to add Co-borrower/Guarantor role and fill their personal information to help me get approval. so that add Co-borrower/Guarantor proactively | SUP | 2019 | S10 | Story |  | M |  |  | 8
| 9-3 | Information notification | c) As a user of eAPP (applicants)I want to add Co-borrower/Guarantor role, due to loan decision told me I have to add Co-borrower/Guarantor role after submission so that get loan approval | SUP | 2019 | S10 | Story |  | M |  |  | 0
| 9-4 | Information notification | d) As a user of eAPP (applicant)I want to be notified about the application statusso that i can proceed with the process. | SUP | 2019 | S10 | Story |  | L |  |  | 0
| 9-5 | CBO/GU information | e) As a user, I want to be notified about the application status, so that I can proceed with the process. | SUP | 2019 | S11 | Story |  | S |  |  | 6
EPIC 10 |  | Document Handling |  | SUP |  |  | EPIC
| 10-1 | Upload files | a) As a user of eAPP (applicants) I want to upload documents so that upload my docs to proceed with the loan application. | SUP | 2019 | S11 | Story |  | L |  |  | 13
| 10-2 | CBO/GU upload files | b) As a co-borrower or guarantorI want to upload the documentsso that I can submit the application together with the main applicant | SUP | 2019 | S11 | Story |  | L |  |  | 13
| 8-3 | file management | c) As a user I want to delete wrongly uploaded documentsso that I can replace it with the right one | SUP | 2019 | S12 | Story |  | S |  |  | 0
| 8-4 | file management | d) As a user I want to see the uploaded documentsso that I know that they have been uploaded | SUP | 2019 | S12 | Story |  | S |  |  | 0
| 8-5 | file management | e) As a user I want to see a list of documents that should be uploadedso that I know what to upload | SUP | 2019 | S12 | Story |  | S |  |  | 0
| 8-6 | File limitation | f) As a admin I want that the user is restricted from uploading the wrong formatsso that only process able documents are uploaded | SUP | 2019 | S12 | Story |  | S |  |  | 0
| 8-7 | Camera function | g) As a user I want to take a picture of the documentsso that I can upload | SUP | 2019 | S12 | Story |  | M |  |  | 0
EPIC 11 |  | Application Submission |  | SUP |  |  | EPIC
| 11-1 | Submit the request TBD | As a user, I want to submit the request, so that I can get approved | SUP | 2019 | S13 | Story |  | M |  |  | 8
| 11-2 | Notification | As a user, I want to get notification, so that I know my status | SUP | 2019 | S13 | Story |  | S |  |  | 6
EPIC 12 |  | Administration of the eApp |  | SUP |  |  | EPIC
| 12-1 | Admin Portal | As a admin, I want to have an admin portal, so that I can do configuration and monitoring there | SUP | 2019 | S13 | Story |  | L |  |  | 0
| 12-2 | Emergency Stop | As BMW SF eAPP Owner, I want to stop the app usage at any time, so that no further applications can be started or progressed. | SUP | 2019 | S13 | Story |  | S |  |  | 0
| 12-3 | Search | As BMW SF eAPP Owner, I want to search requests, so that I can easily find request among all | SUP | 2019 | S14 | Story |  | L |  |  | 13
| 12-4 | Analysis Report | As BMW SF eAPP Owner, I want to see the app usage analysis report, so that I know how many users use the app and how they use the app | SUP | 2019 | S14 | Story |  | M |  |  | 8
| 12-5 | Access management | As BMW SF eAPP Owner, I want to set user access by multiple dimensions, so that I can limit the usage by policies | SUP | 2019 | S14 | Story |  | S |  |  | 6
EPIC 13 |  | General Functions |  | SUP |  |  | EPIC
| 13-1 | Draft | As user, I want to save the application at any time, so that I can resume the process without any duplicate work. | SUP | 2019 | S14 | Story |  | S |  |  | 0
| 13-2 | Sync with DFE | As F&I, I want to sync data with what user input in eApp, so that I can easily pick up and continue the process for the user. | SUP | 2019 | S15 | Story |  | M |  |  | 0
| 13-3 | Get support | As a user, I want to be able to get support in eApp, so that I can get contact with BMW and get support | SUP | 2019 | S15 | Story |  | S |  |  | 0
| 13-4 | Cancllation | As a user, I want to be able to cancel my application during process, so that I can quit the application and make other decisions | SUP | 2019 | S15 | Story |  | M |  |  | 0
| 13-5 | Feedback | As eApp owner, I want to collect customer feedback, so that I can update the app to satisfy customers more | SUP | 2019 | S15 | Story |  | S

## 4. Workpackages
| Onsite |  |  |  | Onsite |  |  |  | Onsite |  |  |  | Onsite
offer values
| 2019 |  |  |  | 2020 |  |  |  | 2021
| Skill Level | PD | Cost | Onetime Cost | Skill Level | PD | Cost | Onetime Cost | Skill Level | PD | Cost | Onetime Cost
License Fee
OCR license |  |  |  | 0
CA Authentication |  |  |  | 0
Face Recognization license |  |  |  | 0
Total License Fee | 0 |  |  |  | 0 |  |  |  | 0
Knowledge Transfer
Transition out from Infosys
Transition In | B2 | 0 | 0
Total Knowledge Transfer | 0 |  |  |  | 0 |  |  |  | 0
| 0 |  |  |  | 0 |  |  |  | 0
| 0 |  |  |  | 0 |  |  |  | 0
Total Package | 0 |  |  |  | 0 |  |  |  | 0
Strukturcheck

## 5. Definitions
Table A - Definition of Skill Levels
Skill Levels DESIGN
D1 | BA, Product Mgr, Project Mgr, Designer, etc | System analysis and conceptional design, Analysis of business processes, Self-contained project controlling, Module training, Subproject management, Process consulting, Solution Consulting, Programm-/System-Design, Optimisation of business processes, Knowledge Management, Preparation of training concepts, Preparing proposals at subproject level, Project quality control, Processing of subprojects, Responsibilities within the given frame work, customization / parameterization of software with no source code impact.
D2 | Architect, Senior Project Mgr, etc | Planning, management and implementation of projects, Budget and team management, Preparing proposals at project level, Design of business case documentation, Responsible for quality management systems in the projects, Project-/Subproject Management, Creation of critical Functional Test Cases and Functional Test Strategy, Design of new methods and procedures, designing and conceptualizing Migration Plans and Disaster Plans, Long term subject matter expert.
D3 | Principle Project Mgr, etc | Management of complex, global and innovative projects, Program Management for design driven projects, Integration and steering of sub-projects.
Skill Levels BUILD
B1 | Developer, Tester, etc | System engineering, Module quality control, Management of sub-projects, Processing of subprojects, Subject matter expert within specific application contexts (mapping of relevant business processes to system design including effort estimations), Solution design and implementation - for both custom build, packaged / COTS software. Responsible for solution integration and integration of applications. Conducts build management and deployment. Hypercare.
B2 | Architect, Senior Developer, Senior Tester, etc | Large Program Management for Build driven projects, Longterm subject matter expert with broad process and technical experience, Engineering of large and complex system clusters including financials, Self-contained project controlling, Complex system integration, Project quality control for complex projects, Planning, management and implementation of projects, Budget and team management, Project-/Subproject Management, guidance of project engineers. Planning of Solution Releases / Builds, Creation of Non Functional Test Concepts and Execution, Performance Tuning, Technical Analysis and code assessments, Conducts build management and deployment in large release clusters.
Table B - Definition of Scale Levels
Scale | Duration (MT)
S | 5~8
M | 8~10
L | 10~15
XL | 15~20
XXL | >20

## 6. Master Data (hidden)
StoryMode | Implementer | Year
Story | BMW | 2018
EPIC | SUP | 2019
2020
2021
Scale Manday
S | 6
M | 8
L | 13
XL | 16
XXL | 28