## Team Members
Name | Profile | GCM Level | IM Contact
Yaroslav | PM/SME | France
Zhao Peng | DevOps & ScrumMaster | Chinese GCM4
Ioannis Bistinas | Data scientist | Netherlands
Jeffrey Lupes | Data engineer/Python developer | Netherlands
Gabriele | developers | Chinese
Fang Qun | developers | Chinese GCM2
Maqbool | Data scientist | Chinese GCM5

## Initial Plan
Item | Due | With | Description
Confirm the scope | 2020-07-02 | Li Hui | Read the documents and present a simple silde to confirm with Li Hui
Contact Chinese team | 2020-07-02 | 3 Chinese members | Talk and set up IM contacts

## Scope
General | refactored CLR module and AI system(Risk Assessment Pipeline)
Breakdown | Item
Dev in either parts of the 2 side/current demo
Dev in the integration
Knowledge Transfer of AI system
Server Migration(AI)
Source code access(github) of AI system
Sprint
Sprint 1 | backlog to be defined | 2020-07-06 | 2020-07-17
Sprint 2 | backlog to be defined | 2020-07-20 | 2020-07-31
Sprint 3 | backlog to be defined | 2020-10-03 | 2020-10-14

## Risk Assement Pipeline
1.1 Risk Assessment Pipeline
Handles all microservices. Minor note: the output for now is JSON instead of XML.
1.2 XML Parser
The XML Parser is the first step. It parses the Manifest XML into JSON format, which will be used in the pipeline.
1.3 Business Preprocessing
The Business Preprocessing is the second step. It can do some preprocessing on each entity of the manifest. It takes in the JSON structure of a particular entity and will output JSON results.
1.4 Business Features
The Business Features are the third (to <n>) step and can extract multiple features from each entity of the manifest. It takes in the JSON structure of a particular entity and will output JSON results. The Business Features is a dynamic flow. If there is a new feature that needs to be introduced to the risk assessment pipeline it will be here. E.g. besides tariff classification we can also use cargo scanning. It is also possible to change the order of the dynamic flow.
1.5 Business Enrichment
The Business Enrichment is the fourth step and is able to do some business enrichment on each entity of the manifest. It takes in the JSON structure of a particular entity, which has been preprocessed and includes the outcomes of the business features and will output JSON results.
1.6 Fraud Detection
The Fraud Detection is the last step and is configurable by the client. It takes in the JSON structure of a particular entity, which has all the information gathered in the previous steps and it will output JSON results.