## Feuil1
Date | Project | Title | Delivery | Description | Duration | Time(optional)
2020-07-02 | General | Overall work setup |  | Settle with general information in the office; Set up the working folders and sort out the information | 1h | 9:00 - 10:00
2020-07-02 | E-biscus | Initial planning |  | Sort out all the informaiton collected; Set up the structure of the work/planning | 2h | 10:00 - 12:00
2020-07-02 | E-biscus | Phone calls |  | with team members(lijianyong, lihui, maqbool, gab, fang qun) and update document | 4h | 1:00 - 5:00
2020-07-02 | Presales | read documents |  | going through the documents | 0.25h | 5:30 - 5:45
2020-07-02 | E-biscus | sum-up the day |  | sum up the information collected from today | 0.5h | 5:00 - 5:30
2020-07-02 | General | Daily meeting |  | Daily meeting | 0.25h | 5:45 - 6:00
2020-07-03 | Presales | Prepare meeting with Tiffany | presales_analysis_silde | Read the documents and prepare the slide and meeting with Tiffany at 13:30 | 4h20m | 9:10 - 13:30
2020-07-03 | Presales | Meeting with Tiffany | actionable | The actionable is Zhao will provide a solution chart, spec and business diagram in early CW28 | 40m | 13:30 - 14:10
2020-07-03 | E-biscus | Coordinate resource | N/A | Contact developers for collaboration work | 1h | 14:00 - 15:00
2020-07-03 | E-biscus | Project Kickoff meeting | meeting minutes | Prepare, participate and summerize Kickoff meeting | 2h | 15:00 - 17:00
2020-07-03 | E-biscus | Project Planning | Planning draft document | Initial draft | 0.5h | 17:30 - 18:00
2020-07-06 | E-biscus | Project Planning | Project org chart | Discuss with team members and create the chart | 0.5h | 9:30 - 10:00
2020-07-06 | E-biscus | Project Management | N/A | Discuss with developers and Lihui for resources and tasks and actionables from the PM | 2h | 10:00 - 12:00
2020-07-06 | E-biscus | Project Management | N/A | 海关清关系统和风控系统培训(Clearance and Risk Control) | 1.25h | 15:00 - 16:15
2020-07-06 | E-biscus | Project Planning | Project Management | Prepare for the daily meeting | 0.5h | 16:30 - 17:00
2020-07-06 | E-biscus | Project Planning | Sprint meeting | with whole team | 1h | 17:00 - 18:30
2020-07-06 | Presales | solution diagram | Solution chart&business Mindchart | Going through the document and draw the chart | 2h | 13:00 - 15:00
2020-07-06 | Presales | solution diagram | Solution chart&business Mindchart | Going through the document and draw the chart | 0.25h | 16:15 - 16:30
Z | E-biscus | Devops | N/A | Work shop with Renyi and Gaberial; Install the Jx and related software; Discussion and trouble shooting | 3.5h
2020-07-07 | E-biscus | Project Management | N/A | Resource utilization matrix; list the unsure points via Email; Scrum meeting | 3.h
2020-07-07 | Presales | solution diagram | 3 charts | Going through the document and draw the chart | 2h;